## Wordle Duel Backlog
ID | User Story / Use Case | Priority | Story Points (Effort) | Acceptance Criteria (Definition of Done) | Status
1 | As a player, I want to create or join a match so I can play against another user. | High | 5 | Matchmaking pairs two players in under 2 seconds. | Done
2 | As a player, I want to take turns submitting six-letter word guesses so the game is fair and turn-based. | High | 8 | Turns alternate correctly between players; server enforces turn order. | To Do
3 | As a player, I want instant feedback on each guess so I can adjust my strategy. | High | 5 | Letters display green/yellow/gray feedback within 0.5 seconds. | To Do
4 | As a player, I want to see when it’s my turn to play so I know when to enter a word. | Medium | 2 | A visible turn indicator updates in real time. | To Do
5 | As a player, I want to know when I win or lose so the match feels complete. | High | 4 | Winner announcement and correct word displayed at end of game. | To Do
6 | As a player, I want to restart or play a rematch so I can continue after finishing a match. | Medium | 3 | “Rematch” button starts a new game with same players. | To Do
7 | As a user, I want to log in securely so my matches and stats are saved. | High | 5 | Authentication succeeds with valid credentials; data saved in database. | Cancelled
8 | As a player, I want to play from a browser without installation so I can access it easily. | Medium | 2 | Application loads successfully from any major browser. | Done
9 | As a tester, I want automated validation of guess logic so I can ensure correctness quickly. | Medium | 3 | Unit tests pass for all valid/invalid word conditions. | To Do