## Sprint Backlog
Sprint Goal | User Story | Task | Assigned To | Status | Notes
Sprint 1 Goal: Core Setup | As a player, I want to create or join a match so I can play against another user. | Set up basic project structure and matchmaking endpoints. | Tyler | Completed
Sprint 1 Goal: Core Setup | As a player, I want instant feedback on each guess so I can adjust my strategy. | Implement six-letter word validation and color-coded feedback logic. | Seth | Completed | Add notes here
Sprint 2 Goal: Multiplayer Logic | As a player, I want to take turns submitting six-letter word guesses so the game is fair and turn-based. | Develop backend logic for turn switching and submission control. | Tyler | Completed | Add notes here
Sprint 2 Goal: Multiplayer Logic | As a player, I want to see when it’s my turn to play so I know when to enter a word. | Add visual turn indicators and WebSocket communication for turns. | Tyler | Completed | Add notes here
Sprint 2 Goal: Multiplayer Logic | As a player, I want to know when I win or lose so the match feels complete. | Implement win detection and results screen display. | Seth | Completed | Add notes here
Sprint 2 Goal: Multiplayer Logic | As a player, I want to restart or play a rematch so I can continue after finishing a match. | Add rematch and replay functionality between same players. | Seth | To Do | Add notes here
Sprint 3 Goal: User Interface | As a user, I want to log in securely. | Develop and connect login and authentication modules. | Tyler | Cancelled | Add notes here
Sprint 3 Goal: User Interface | As a player, I want to play from a browser without installation so I can access it easily. | Ensure responsive layout and browser compatibility. | Seth | Completed | Add notes here
Sprint 4 Goal: Optimization & Deployment | As a tester, I want automated validation of guess logic so I can ensure correctness quickly. | Conduct final testing, debugging, and deployment to cloud. | Tyler/Seth | To Do | Add notes here